## Phase 1
Actual Hours Spent
| Task | Estimate(hours) | Resources | Documenting | Coding | Total
Requirements analysis | Functional requirements gathering | 3 | 1 | 1 | 0 | 2
| Non-Functional requirements gathering | 3 | 0.5 | 0.5 | 0 | 1
Requirements specifications | Functional requirements specification | 6 | 2 | 3 | 0 | 5
| Non-Functional requirements specification | 6 | 0.5 | 2 | 0 | 2.5
Software design | Supporting diagrams | 5 | 2.5 | 3 | 0 | 5.5
| Database structure diagram | 3 | 4 | 0.5 | 2 | 6.5
Software coding | Create Database | 10 | 1 | 0 | 3 | 4
| Create Add, Update, Remove stored procedures | 8 | 0.5 | 0 | 4 | 4.5
| Create clothing interface | 30 | 10 | 1 | 8 | 19
| Create admin clothing interface | 20 | 5 | 1 | 3 | 9
| Create food interface | 30 | 2 | 1 | 3 | 6
| Create admin food interface | 20 | 2 | 1 | 4 | 7
| Create search functinality | 15 |  |  |  | 0
| Create browse functionality | 5 |  |  |  | 0
| Create filter functionality | 10 |  |  |  | 0
| Create specials functionality | 4 | 2 | 0 |  | 2
| Add test data | 5 | 6 | 0 | 2 | 8
| Download images | 4 | 2 | 0 | 0 | 2
| Add website images | 3 | 0 | 1 | 1 | 2
Software testing | Create test cases | 15 |  |  |  | 0
| Execute test cases | 5 |  |  |  | 0
| Update code based on test cases | 10 |  |  |  | 0
| End-to-End testing | 5 |  |  |  | 0
Software and tools gathering | Download tools | 5 | 3 | 0 | 0 | 3
TOTAL |  | 230

## Phase 2
Actual Hours Spent
| Task | Estimate(hours) | Resources | Documenting | Coding | Total
Requirements analysis | Functional requirements gathering | 1 | 0 | 1 | 0 | 1
| Non-Functional requirements gathering | 1 | 0 | 0.5 | 0 | 0.5
Requirements specifications | Functional requirements specification | 1 | 0 | 1 | 0 | 1
| Non-Functional requirements specification | 1 | 0 | 0.75 | 0 | 0.75
Software design | Supporting diagrams | 1 | 0 | 0 | 0.5 | 0.5
| Updated database structure diagram | 1 | 0 |  | 0 | 0
Software coding | Create Database tables for the user and cart functionality | 2 | 0 | 0 | 1.5 | 1.5
| Create Add, Update, Remove stored procedures for user and cart | 4 | 0 | 0 | 6 | 6
| Create user registration interface | 10 | 2 | 0 | 3 | 5
| Create user profile updating interface | 5 | 0 |  |  | 0
| Create cart functionality | 10 | 5 | 1 | 15 | 21
| Create electronic payment functionality | 5 | 1 | 0 | 0 | 1
| Download images for user profiles | 1 | 0 | 0 | 0 | 0
| Create test cases | 5 | 0 | 0 | 2 | 2
| Execute test cases | 1 | 0 | 0 | 1 | 1
| Update code based on test cases | 2 | 0 | 0 | 2 | 2
| End-to-End testing | 5 | 0 | 0 | 3.5 | 3.5
TOTAL |  | 56

## Complexity Report
General Comment: The calculations were created using the following modules: model, repository, controller, main. Generally each module contains at least one class e.g. the model module contains the ProductItem. Admin and Special classes.
Metric | Phase 1 | Phase 2 | Comments_Phase1 | Comments_Phase2
Structural Complexity | 11 |  | Value is the sum of the fan-out value squared for all the modules
Data Complexity | 0.41667 |  | Calculated based on the name and id input variables that are accepted by each module. e.g. name can be passed to the model module to receive a user with that name
System Complexity | 11.4167
Cohesion | 0
Coupling | 0
Cyclomatic Complexity | 1 |  | Current main function only calls the applications run function.